## Sheet 1
id | name | type | owner | partsnumber | assembly | shortname | longname | link | cost | totalreqs | status | PlannedStartDate | PlannedEndDate | Duration
A.01 | Body Assembly | Assembly | Mechanical Subsystem | [7 empty] | open | 2023-08-30 | 2025-08-28 | 730
A.02 | Drive Wheel Assembly-1 | Assembly | Mobility Subsystem | [7 empty] | open | 2023-08-30 | 2025-08-28 | 730
A.03 | Drive Wheel Assembly-2 | Assembly | Mobility Subsystem | [7 empty] | open | 2023-08-30 | 2025-08-28 | 730
A.04 | Corner Wheel Assembly-1 | Assembly | Mobility Subsystem | [7 empty] | open | 2023-08-30 | 2025-08-28 | 730
A.05 | Corner Wheel Assembly-2 | Assembly | Mobility Subsystem | [7 empty] | open | 2023-08-30 | 2025-08-28 | 730
A.06 | Corner Wheel Assembly-3 | Assembly | Mobility Subsystem | [7 empty] | open | 2023-08-30 | 2025-08-28 | 730
A.07 | Corner Wheel Assembly-4 | Assembly | Mobility Subsystem | [7 empty] | open | 2023-08-30 | 2025-08-28 | 730
A.08 | Rocker Bogie Suspension Assembly-1 | Assembly | Mechanical Subsystem | [7 empty] | open | 2023-08-30 | 2025-08-28 | 730
A.09 | Rocker Bogie Suspension Assembly-2 | Assembly | Mechanical Subsystem | [7 empty] | open | 2023-08-30 | 2025-08-28 | 730
A.10 | Mechanical Harness | Assembly | Mechanical Subsystem | [7 empty] | open | 2023-08-30 | 2025-08-28 | 730
C.01 | Rover System | System | [8 empty] | open | 2023-08-30 | 2025-08-28 | 730
C.01.01 | Mechanical Subsystem | Subsystem | Rover System | [7 empty] | open | 2023-08-30 | 2025-08-28 | 730
C.01.02 | Power Subsystem | Subsystem | Rover System | [7 empty] | open | 2023-08-30 | 2025-08-28 | 730
C.01.03 | Mobility Subsystem | Subsystem | Rover System | [7 empty] | open | 2023-08-30 | 2025-08-28 | 730
C.01.04 | Control Subsystem | Subsystem | Rover System | [7 empty] | open | 2023-08-30 | 2025-08-28 | 730
C.01.05 | Navigation Subsystem | Subsystem | Rover System | [7 empty] | open | 2023-08-30 | 2025-08-28 | 730
C.01.06 | CDH Subsystem | Subsystem | Rover System | [7 empty] | open | 2023-08-30 | 2025-08-28 | 730
P0.001 | 120mm open goRail-1 | Part | Body Assembly | 1118-0024-0120 | body | 120mm open goRail | 1118 Series Open goRAIL (120mm Length) - goBILDA | https://www.gobilda.com/1118-series-open-gorail-120mm-length/ | $4.99 | 2 | ongoing | 2023-10-01 | 2025-08-28 | 698
P0.002 | 120mm open goRail-2 | Part | Body Assembly | 1118-0024-0120 | body | 120mm open goRail | 1118 Series Open goRAIL (120mm Length) - goBILDA | https://www.gobilda.com/1118-series-open-gorail-120mm-length/ | $4.99 | 2 | ongoing | 2023-10-01 | 2025-08-28 | 698
P0.003 | 2 Hole U channel-1 | Part | Body Assembly | 1120-0002-0072 | drive wheel,body | 2 Hole U channel | 1120 Series U-Channel (2 Hole, 72mm Length) - goBILDA | https://www.gobilda.com/1120-series-u-channel-2-hole-72mm-length/ | $4.99 | 14 | ongoing | 2023-10-01 | 2025-08-28 | 698
P0.004 | 2 Hole U channel-2 | Part | Body Assembly | 1120-0002-0072 | drive wheel,body | 2 Hole U channel | 1120 Series U-Channel (2 Hole, 72mm Length) - goBILDA | https://www.gobilda.com/1120-series-u-channel-2-hole-72mm-length/ | $4.99 | 14 | ongoing | 2023-10-01 | 2025-08-28 | 698
P0.005 | 32mm bearing-1 | Part | Body Assembly | 1604-0043-0032 | body | 32mm bearing | 1604 Series 2-Side, 2-Post Pillow Block (32mm Bore) - goBILDA | https://www.gobilda.com/1604-series-2-side-2-post-pillow-block-32mm-bore/ | $12.99 | 4 | ongoing | 2023-10-01 | 2025-08-28 | 698
P0.006 | 32mm bearing-2 | Part | Body Assembly | 1604-0043-0032 | body | 32mm bearing | 1604 Series 2-Side, 2-Post Pillow Block (32mm Bore) - goBILDA | https://www.gobilda.com/1604-series-2-side-2-post-pillow-block-32mm-bore/ | $12.99 | 4 | ongoing | 2023-10-01 | 2025-08-28 | 698
P0.007 | 32mm bearing-3 | Part | Body Assembly | 1604-0043-0032 | body | 32mm bearing | 1604 Series 2-Side, 2-Post Pillow Block (32mm Bore) - goBILDA | https://www.gobilda.com/1604-series-2-side-2-post-pillow-block-32mm-bore/ | $12.99 | 4 | ongoing | 2023-10-01 | 2025-08-28 | 698
P0.008 | 32mm bearing-4 | Part | Body Assembly | 1604-0043-0032 | body | 32mm bearing | 1604 Series 2-Side, 2-Post Pillow Block (32mm Bore) - goBILDA | https://www.gobilda.com/1604-series-2-side-2-post-pillow-block-32mm-bore/ | $12.99 | 4 | ongoing | 2023-10-01 | 2025-08-28 | 698
P0.009 | 32mm 6mm spacer 2 pack-1 | Part | Body Assembly | 1506-0032-0006 | body | 32mm 6mm spacer 2 pack | 1506 Series 32mm ID Spacer (36mm OD, 6mm Length) - 2 Pack - goBILDA | https://www.gobilda.com/1506-series-32mm-id-spacer-36mm-od-6mm-length-2-pack/ | $3.49 | 3 | ongoing | 2023-10-01 | 2025-08-28 | 698
P0.010 | 32mm 6mm spacer 2 pack-2 | Part | Body Assembly | 1506-0032-0006 | body | 32mm 6mm spacer 2 pack | 1506 Series 32mm ID Spacer (36mm OD, 6mm Length) - 2 Pack - goBILDA | https://www.gobilda.com/1506-series-32mm-id-spacer-36mm-od-6mm-length-2-pack/ | $3.49 | 3 | ongoing | 2023-10-01 | 2025-08-28 | 698
P0.011 | 32mm 6mm spacer 2 pack-3 | Part | Body Assembly | 1506-0032-0006 | body | 32mm 6mm spacer 2 pack | 1506 Series 32mm ID Spacer (36mm OD, 6mm Length) - 2 Pack - goBILDA | https://www.gobilda.com/1506-series-32mm-id-spacer-36mm-od-6mm-length-2-pack/ | $3.49 | 3 | ongoing | 2023-10-01 | 2025-08-28 | 698
P0.012 | 29 hole beam-1 | Part | Body Assembly | 1106-0029-0232 | body | 29 hole beam | 1106 Series Square Beam (29 Hole, 232mm Length) - goBILDA | https://www.gobilda.com/1106-series-square-beam-29-hole-232mm-length/ | $5.09 | 5 | ongoing | 2023-10-01 | 2025-08-28 | 698
P0.013 | 29 hole beam-2 | Part | Body Assembly | 1106-0029-0232 | body | 29 hole beam | 1106 Series Square Beam (29 Hole, 232mm Length) - goBILDA | https://www.gobilda.com/1106-series-square-beam-29-hole-232mm-length/ | $5.09 | 5 | ongoing | 2023-10-01 | 2025-08-28 | 698
P0.014 | 29 hole beam-3 | Part | Body Assembly | 1106-0029-0232 | body | 29 hole beam | 1106 Series Square Beam (29 Hole, 232mm Length) - goBILDA | https://www.gobilda.com/1106-series-square-beam-29-hole-232mm-length/ | $5.09 | 5 | ongoing | 2023-10-01 | 2025-08-28 | 698
P0.015 | 29 hole beam-4 | Part | Body Assembly | 1106-0029-0232 | body | 29 hole beam | 1106 Series Square Beam (29 Hole, 232mm Length) - goBILDA | https://www.gobilda.com/1106-series-square-beam-29-hole-232mm-length/ | $5.09 | 5 | ongoing | 2023-10-01 | 2025-08-28 | 698
P0.016 | 29 hole beam-5 | Part | Body Assembly | 1106-0029-0232 | body | 29 hole beam | 1106 Series Square Beam (29 Hole, 232mm Length) - goBILDA | https://www.gobilda.com/1106-series-square-beam-29-hole-232mm-length/ | $5.09 | 5 | ongoing | 2023-10-01 | 2025-08-28 | 698
P0.017 | 41 hole beam-1 | Part | Body Assembly | 1106-0041-0328 | body | 41 hole beam | 1106 Series Square Beam (41 Hole, 328mm Length) - goBILDA | https://www.gobilda.com/1106-series-square-beam-41-hole-328mm-length/ | $6.99 | 4 | ongoing | 2023-10-01 | 2025-08-28 | 698
P0.018 | 41 hole beam-2 | Part | Body Assembly | 1106-0041-0328 | body | 41 hole beam | 1106 Series Square Beam (41 Hole, 328mm Length) - goBILDA | https://www.gobilda.com/1106-series-square-beam-41-hole-328mm-length/ | $6.99 | 4 | ongoing | 2023-10-01 | 2025-08-28 | 698
P0.019 | 41 hole beam-3 | Part | Body Assembly | 1106-0041-0328 | body | 41 hole beam | 1106 Series Square Beam (41 Hole, 328mm Length) - goBILDA | https://www.gobilda.com/1106-series-square-beam-41-hole-328mm-length/ | $6.99 | 4 | closed | 2023-08-30 | 2023-12-30 | 123
P0.020 | 41 hole beam-4 | Part | Body Assembly | 1106-0041-0328 | body | 41 hole beam | 1106 Series Square Beam (41 Hole, 328mm Length) - goBILDA | https://www.gobilda.com/1106-series-square-beam-41-hole-328mm-length/ | $6.99 | 4 | closed | 2023-08-30 | 2023-12-30 | 123
P0.021 | 12 hole beam-1 | Part | Body Assembly | 1106-0012-0096 | body | 12 hole beam | 1106 Series Square Beam (12 Hole, 96mm Length) - goBILDA | https://www.gobilda.com/1106-series-square-beam-12-hole-96mm-length/ | $2.99 | 8 | closed | 2023-08-30 | 2023-12-30 | 123
P0.022 | 12 hole beam-2 | Part | Body Assembly | 1106-0012-0096 | body | 12 hole beam | 1106 Series Square Beam (12 Hole, 96mm Length) - goBILDA | https://www.gobilda.com/1106-series-square-beam-12-hole-96mm-length/ | $2.99 | 8 | closed | 2023-08-30 | 2023-12-30 | 123
P0.023 | 12 hole beam-3 | Part | Body Assembly | 1106-0012-0096 | body | 12 hole beam | 1106 Series Square Beam (12 Hole, 96mm Length) - goBILDA | https://www.gobilda.com/1106-series-square-beam-12-hole-96mm-length/ | $2.99 | 8 | closed | 2023-08-30 | 2023-12-30 | 123
P0.024 | 12 hole beam-4 | Part | Body Assembly | 1106-0012-0096 | body | 12 hole beam | 1106 Series Square Beam (12 Hole, 96mm Length) - goBILDA | https://www.gobilda.com/1106-series-square-beam-12-hole-96mm-length/ | $2.99 | 8 | closed | 2023-08-30 | 2023-12-30 | 123
P0.025 | 12 hole beam-5 | Part | Body Assembly | 1106-0012-0096 | body | 12 hole beam | 1106 Series Square Beam (12 Hole, 96mm Length) - goBILDA | https://www.gobilda.com/1106-series-square-beam-12-hole-96mm-length/ | $2.99 | 8 | closed | 2023-08-30 | 2023-12-30 | 123
P0.026 | 12 hole beam-6 | Part | Body Assembly | 1106-0012-0096 | body | 12 hole beam | 1106 Series Square Beam (12 Hole, 96mm Length) - goBILDA | https://www.gobilda.com/1106-series-square-beam-12-hole-96mm-length/ | $2.99 | 8 | closed | 2023-08-30 | 2023-12-30 | 123
P0.027 | 12 hole beam-7 | Part | Body Assembly | 1106-0012-0096 | body | 12 hole beam | 1106 Series Square Beam (12 Hole, 96mm Length) - goBILDA | https://www.gobilda.com/1106-series-square-beam-12-hole-96mm-length/ | $2.99 | 8 | closed | 2023-08-30 | 2023-12-30 | 123
P0.028 | 12 hole beam-8 | Part | Body Assembly | 1106-0012-0096 | body | 12 hole beam | 1106 Series Square Beam (12 Hole, 96mm Length) - goBILDA | https://www.gobilda.com/1106-series-square-beam-12-hole-96mm-length/ | $2.99 | 8 | closed | 2023-08-30 | 2023-12-30 | 123
P0.029 | 41 hole u-beam beam-1 | Part | Body Assembly | 1101-0041-0328 | body | 41 hole u-beam beam | 1101 Series U-Beam (41 Hole, 328mm Length) - goBILDA | https://www.gobilda.com/1101-series-u-beam-41-hole-328mm-length/ | $3.89 | 1 | closed | 2023-08-30 | 2023-12-30 | 123
P0.030 | 7 hole flat beam 2pack-1 | Part | Body Assembly | 1102-0007-0056 | body | 7 hole flat beam 2pack | 1102 Series Flat Beam (7 Hole, 56mm Length) - 2 Pack - goBILDA | https://www.gobilda.com/1102-series-flat-beam-7-hole-56mm-length-2-pack/ | $2.49 | 2 | closed | 2023-08-30 | 2023-12-30 | 123
P0.031 | 7 hole flat beam 2pack-2 | Part | Body Assembly | 1102-0007-0056 | body | 7 hole flat beam 2pack | 1102 Series Flat Beam (7 Hole, 56mm Length) - 2 Pack - goBILDA | https://www.gobilda.com/1102-series-flat-beam-7-hole-56mm-length-2-pack/ | $2.49 | 2 | closed | 2023-08-30 | 2023-12-30 | 123
P0.032 | dual block mount-1 | Part | Body Assembly | 1205-0001-0004 | body | dual block mount | 1205 Series Dual Block Mount (1-4) - 2 Pack - goBILDA | https://www.gobilda.com/1205-series-dual-block-mount-1-4-2-pack/ | $5.99 | 2 | closed | 2023-08-30 | 2023-12-30 | 123
P0.033 | dual block mount-2 | Part | Body Assembly | 1205-0001-0004 | body | dual block mount | 1205 Series Dual Block Mount (1-4) - 2 Pack - goBILDA | https://www.gobilda.com/1205-series-dual-block-mount-1-4-2-pack/ | $5.99 | 2 | closed | 2023-08-30 | 2023-12-30 | 123
P0.034 | 90deg threaded gusset 4pack-1 | Part | Body Assembly | 1203-0001-0001 | body | 90deg threaded gusset 4pack | 1203 Series Block Mount (1-1) - 4 Pack - goBILDA | https://www.gobilda.com/1203-series-block-mount-1-1-4-pack/ | $4.99 | 1 | closed | 2023-08-30 | 2023-12-30 | 123
P0.035 | 50mm threaded rod-1 | Part | Body Assembly | 2808-0004-0050 | body | 50mm threaded rod | 2808 Series Stainless Steel Threaded Rod (M4 x 0.7mm, 50mm Length) - 2 Pack - goBILDA | https://www.gobilda.com/2808-series-stainless-steel-threaded-rod-m4-x-0-7mm-50mm-length-2-pack/ | $1.49 | 1 | closed | 2023-08-30 | 2023-12-30 | 123
P0.036 | ball linkage 2pack-1 | Part | Body Assembly | 2913-0004-0241 | body | ball linkage 2pack | 2913 Series Steel Ball Linkage (Female M4 x 0.7mm, 24.1mm Length) - 2 Pack - goBILDA | https://www.gobilda.com/2913-series-steel-ball-linkage-female-m4-x-0-7mm-24-1mm-length-2-pack/ | $4.99 | 2 | closed | 2023-08-30 | 2023-12-30 | 123
P0.037 | ball linkage 2pack-2 | Part | Body Assembly | 2913-0004-0241 | body | ball linkage 2pack | 2913 Series Steel Ball Linkage (Female M4 x 0.7mm, 24.1mm Length) - 2 Pack - goBILDA | https://www.gobilda.com/2913-series-steel-ball-linkage-female-m4-x-0-7mm-24-1mm-length-2-pack/ | $4.99 | 2 | closed | 2023-08-30 | 2023-12-30 | 123
P0.038 | Idler Bearing Hub-1 | Part | Body Assembly | 1608-0001-0001 | body | Idler Bearing Hub | Idler Bearing-Hub (32mm OD, 16mm Height) - goBILDA | https://www.gobilda.com/idler-bearing-hub-32mm-od-16mm-height/ | $12.99 | 1 | closed | 2023-08-30 | 2023-12-30 | 123
P0.039 | plastic hinges-1 | Part | Body Assembly | 2902-0003-0001 | body | plastic hinges | Plastic Hinge - 2 Pack - goBILDA | https://www.gobilda.com/plastic-hinge-2-pack/ | $4.99 | 2 | closed | 2023-08-30 | 2023-12-30 | 123
P0.040 | plastic hinges-2 | Part | Body Assembly | 2902-0003-0001 | body | plastic hinges | Plastic Hinge - 2 Pack - goBILDA | https://www.gobilda.com/plastic-hinge-2-pack/ | $4.99 | 2 | closed | 2023-08-30 | 2023-12-30 | 123
P0.041 | 8mm standoffs-1 | Part | Body Assembly | 1501-0006-0080 | body | 8mm standoffs | 1501 Series M4 x 0.7mm Standoff (6mm OD, 8mm Length) - 4 Pack | https://www.gobilda.com/1501-series-m4-x-0-7mm-standoff-6mm-od-8mm-length-4-pack/ | $2.49 | 2 | closed | 2023-08-30 | 2023-12-30 | 123
P0.042 | 8mm standoffs-2 | Part | Body Assembly | 1501-0006-0080 | body | 8mm standoffs | 1501 Series M4 x 0.7mm Standoff (6mm OD, 8mm Length) - 4 Pack | https://www.gobilda.com/1501-series-m4-x-0-7mm-standoff-6mm-od-8mm-length-4-pack/ | $2.49 | 2 | closed | 2023-08-30 | 2023-12-30 | 123
P0.043 | 22mm standoffs-1 | Part | Body Assembly | 1501-0006-0220 | body | 22mm standoffs | 1501 Series M4 x 0.7mm Standoff (6mm OD, 22mm Length) - 4 Pack | https://www.gobilda.com/1501-series-m4-x-0-7mm-standoff-6mm-od-22mm-length-4-pack/ | $3.49 | 2 | closed | 2023-08-30 | 2023-12-30 | 123
P0.044 | 22mm standoffs-2 | Part | Body Assembly | 1501-0006-0220 | body | 22mm standoffs | 1501 Series M4 x 0.7mm Standoff (6mm OD, 22mm Length) - 4 Pack | https://www.gobilda.com/1501-series-m4-x-0-7mm-standoff-6mm-od-22mm-length-4-pack/ | $3.49 | 2 | closed | 2023-08-30 | 2023-12-30 | 123
P0.045 | plastic spacer-1 | Part | Body Assembly | 1500-0010-0006 | body | plastic spacer | 1500 Series Plastic Spacer (6mm ID x 8mm OD, 1mm Thickness) - 12 Pack | https://www.gobilda.com/1500-series-plastic-spacer-6mm-id-x-8mm-od-1mm-thickness-12-pack/ | $2.79 | 1 | closed | 2023-08-30 | 2023-12-30 | 123
P0.046 | 3x5 grid plate-1 | Part | Body Assembly | 1116-0024-0040 | rocker bogie,body | 3x5 grid plate | 1116 Series Grid Plate (3 x 5 Hole, 24 x 40mm) - goBILDA | https://www.gobilda.com/1116-series-grid-plate-3-x-5-hole-24-x-40mm/ | $1.29 | 8 | closed | 2023-08-30 | 2023-12-30 | 123
P0.047 | 3x5 grid plate-2 | Part | Body Assembly | 1116-0024-0040 | rocker bogie,body | 3x5 grid plate | 1116 Series Grid Plate (3 x 5 Hole, 24 x 40mm) - goBILDA | https://www.gobilda.com/1116-series-grid-plate-3-x-5-hole-24-x-40mm/ | $1.29 | 8 | closed | 2023-08-30 | 2023-12-30 | 123
P0.048 | 3x5 grid plate-3 | Part | Body Assembly | 1116-0024-0040 | rocker bogie,body | 3x5 grid plate | 1116 Series Grid Plate (3 x 5 Hole, 24 x 40mm) - goBILDA | https://www.gobilda.com/1116-series-grid-plate-3-x-5-hole-24-x-40mm/ | $1.29 | 8 | closed | 2023-08-30 | 2023-12-30 | 123
P0.049 | 3x5 grid plate-4 | Part | Body Assembly | 1116-0024-0040 | rocker bogie,body | 3x5 grid plate | 1116 Series Grid Plate (3 x 5 Hole, 24 x 40mm) - goBILDA | https://www.gobilda.com/1116-series-grid-plate-3-x-5-hole-24-x-40mm/ | $1.29 | 8 | closed | 2023-08-30 | 2023-12-30 | 123
P0.050 | 2 hole flat beam-1 | Part | Body Assembly | 1102-0002-0016 | body | 2 hole flat beam | 1102 Series Flat Beam (2 Hole, 16mm Length) - 2 Pack | https://www.gobilda.com/1102-series-flat-beam-2-hole-16mm-length-2-pack/ | $1.79 | 2 | closed | 2023-08-30 | 2023-12-30 | 123
P0.051 | 2 hole flat beam-2 | Part | Body Assembly | 1102-0002-0016 | body | 2 hole flat beam | 1102 Series Flat Beam (2 Hole, 16mm Length) - 2 Pack | https://www.gobilda.com/1102-series-flat-beam-2-hole-16mm-length-2-pack/ | $1.79 | 2 | closed | 2023-08-30 | 2023-12-30 | 123
P1.001 | wheel-1 | Part | Drive Wheel Assembly-1 | 5374X | drive wheel | wheel | Traxxas 5374X Talon Tires, Gemini Wheels, Black Chrome - Dollar Hobbyz | https://www.dollarhobbyz.com/collections/all/products/traxxas-2-talon-tires-gemini-black-chrome-wheels-5374x | $34.95 | 3 | closed | 2023-08-30 | 2023-12-30 | 123
P1.002 | clamping mount-1 | Part | Drive Wheel Assembly-1 | 1401-0043-0036 | drive wheel | clamping mount | 1401 Series 2-Side, 2-Post Clamping Mount (43mm Width, 36mm Bore) - goBILDA | https://www.gobilda.com/1401-series-2-side-2-post-clamping-mount-43mm-width-36mm-bore/ | $6.99 | 6 | closed | 2023-08-30 | 2023-12-30 | 123
P1.003 | motor-1 | Part | Drive Wheel Assembly-1 | 5203-2402-0027 | drive wheel | motor | 5203 Series Yellow Jacket Planetary Gear Motor (26.9:1 Ratio, 24mm Length 8mm REX™ Shaft, 223 RPM, 3.3 - 5V Encoder) | https://www.gobilda.com/5203-series-yellow-jacket-planetary-gear-motor-26-9-1-ratio-24mm-length-8mm-rex-shaft-223-rpm-3-3-5v-encoder/ | $42.99 | 6 | closed | 2023-08-30 | 2023-12-30 | 123
P1.004 | REX bore hub-1 | Part | Drive Wheel Assembly-1 | 1310-0016-4008 | drive wheel | REX bore hub | 1310 Series Hyper Hub (8mm REX™ Bore) | https://www.gobilda.com/1310-series-hyper-hub-8mm-rex-bore/ | $7.99 | 6 | closed | 2023-08-30 | 2023-12-30 | 123
P1.005 | 2 Hole U channel-1 | Part | Drive Wheel Assembly-1 | 1120-0002-0072 | drive wheel,body | 2 Hole U channel | 1120 Series U-Channel (2 Hole, 72mm Length) - goBILDA | https://www.gobilda.com/1120-series-u-channel-2-hole-72mm-length/ | $4.99 | 14 | ongoing | 2023-10-01 | 2024-01-31 | 123
P10.001 | hurricane nuts-1 | Part | Mechanical Harness | 2805-0004-0108 | general | hurricane nuts | Hurricane Nut for goRAIL - 25 Pack - goBILDA | https://www.gobilda.com/hurricane-nut-for-gorail-25-pack/ | $9.99 | 1 | ongoing | 2023-10-01 | 2024-01-31 | 123
P10.002 | wire grommets-1 | Part | Mechanical Harness | 2911-0014-0001 | general | wire grommets | Plastic Grommet (14-1) - 12 Pack - goBILDA | https://www.gobilda.com/plastic-grommet-14-1-12-pack/ | $1.99 | 1 | ongoing | 2023-10-01 | 2024-01-31 | 123
P10.003 | M4 washers-1 | Part | Mechanical Harness | 2801-0004-0008 | general | M4 washers | Zinc Plates Steel Washer (M4 x 8mm OD) - 25 Pack - goBILDA | https://www.gobilda.com/2801-series-zinc-plated-steel-washer-4mm-id-x-8mm-od-25-pack/ | $1.99 | 1 | ongoing | 2023-10-01 | 2024-01-31 | 123
P10.004 | M4 nuts-1 | Part | Mechanical Harness | 2811-0004-0007 | general | M4 nuts | Zinc Plates Steel Hex Nut (M4 x 7) - 25 Pack - goBILDA | https://www.gobilda.com/2811-series-zinc-plated-steel-hex-nut-m4-x-0-7mm-7mm-hex-25-pack/ | $2.49 | 1 | ongoing | 2023-10-01 | 2024-01-31 | 123
P10.005 | M4 locknuts-1 | Part | Mechanical Harness | 2812-0004-0007 | general | M4 locknuts | Zinc Plates Steel Locknut (M4 x 7) - 25 Pack - goBILDA | https://www.gobilda.com/2812-series-zinc-plated-steel-nylon-insert-locknut-m4-x-0-7mm-7mm-hex-25-pack/ | $2.99 | 1 | ongoing | 2023-10-01 | 2024-01-31 | 123
P10.006 | M4x6 button screws-1 | Part | Mechanical Harness | 2802-0004-0006 | general | M4x6 button screws | M4x6 Button Screw 25-pack | https://www.gobilda.com/2802-series-zinc-plated-steel-button-head-screw-m4-x-0-7mm-6mm-length-25-pack/ | $2.99 | 2 | ongoing | 2023-10-01 | 2024-01-31 | 123
P10.007 | M4x6 button screws-2 | Part | Mechanical Harness | 2802-0004-0006 | general | M4x6 button screws | M4x6 Button Screw 25-pack | https://www.gobilda.com/2802-series-zinc-plated-steel-button-head-screw-m4-x-0-7mm-6mm-length-25-pack/ | $2.99 | 2 | ongoing | 2023-10-01 | 2024-01-31 | 123
P10.008 | M4x10 button screws-1 | Part | Mechanical Harness | 2802-0004-0010 | general | M4x10 button screws | M4x10 Button Screw 25-pack | https://www.gobilda.com/2802-series-zinc-plated-steel-button-head-screw-m4-x-0-7mm-10mm-length-25-pack/ | $3.39 | 3 | ongoing | 2023-10-01 | 2024-01-31 | 123
P10.009 | M4x10 button screws-2 | Part | Mechanical Harness | 2802-0004-0010 | general | M4x10 button screws | M4x10 Button Screw 25-pack | https://www.gobilda.com/2802-series-zinc-plated-steel-button-head-screw-m4-x-0-7mm-10mm-length-25-pack/ | $3.39 | 3 | ongoing | 2023-10-01 | 2024-01-31 | 123
P10.010 | M4x10 button screws-3 | Part | Mechanical Harness | 2802-0004-0010 | general | M4x10 button screws | M4x10 Button Screw 25-pack | https://www.gobilda.com/2802-series-zinc-plated-steel-button-head-screw-m4-x-0-7mm-10mm-length-25-pack/ | $3.39 | 3 | ongoing | 2023-10-01 | 2024-01-31 | 123
P10.011 | M4x16 button screws-1 | Part | Mechanical Harness | 2802-0004-0016 | general | M4x16 button screws | M4x16 Button Screw 25-pack | https://www.gobilda.com/2802-series-zinc-plated-steel-button-head-screw-m4-x-0-7mm-16mm-length-25-pack/ | $3.79 | 2 | ongoing | 2023-10-01 | 2024-01-31 | 123
P10.012 | M4x16 button screws-2 | Part | Mechanical Harness | 2802-0004-0016 | general | M4x16 button screws | M4x16 Button Screw 25-pack | https://www.gobilda.com/2802-series-zinc-plated-steel-button-head-screw-m4-x-0-7mm-16mm-length-25-pack/ | $3.79 | 2 | ongoing | 2023-10-01 | 2024-01-31 | 123
P10.013 | M4x8 socket screws-1 | Part | Mechanical Harness | 2800-0004-0008 | general | M4x8 socket screws | M4x8 Socket Screw 25-pack | https://www.gobilda.com/2800-series-zinc-plated-steel-socket-head-screw-m4-x-0-7mm-8mm-length-25-pack/ | $3.19 | 2 | ongoing | 2023-10-01 | 2024-01-31 | 123
P10.014 | M4x8 socket screws-2 | Part | Mechanical Harness | 2800-0004-0008 | general | M4x8 socket screws | M4x8 Socket Screw 25-pack | https://www.gobilda.com/2800-series-zinc-plated-steel-socket-head-screw-m4-x-0-7mm-8mm-length-25-pack/ | $3.19 | 2 | ongoing | 2023-10-01 | 2024-01-31 | 123
P10.015 | M4x10 socket screws-1 | Part | Mechanical Harness | 2800-0004-0010 | general | M4x10 socket screws | M4x10 Socket Screw 25-pack | https://www.gobilda.com/2800-series-zinc-plated-steel-socket-head-screw-m4-x-0-7mm-10mm-length-25-pack/ | $3.19 | 3 | ongoing | 2023-10-01 | 2024-01-31 | 123
P10.016 | M4x10 socket screws-2 | Part | Mechanical Harness | 2800-0004-0010 | general | M4x10 socket screws | M4x10 Socket Screw 25-pack | https://www.gobilda.com/2800-series-zinc-plated-steel-socket-head-screw-m4-x-0-7mm-10mm-length-25-pack/ | $3.19 | 3 | ongoing | 2023-10-01 | 2024-01-31 | 123
P10.017 | M4x10 socket screws-3 | Part | Mechanical Harness | 2800-0004-0010 | general | M4x10 socket screws | M4x10 Socket Screw 25-pack | https://www.gobilda.com/2800-series-zinc-plated-steel-socket-head-screw-m4-x-0-7mm-10mm-length-25-pack/ | $3.19 | 3 | ongoing | 2023-10-01 | 2024-01-31 | 123
P10.018 | M4x1２ socket screws-1 | Part | Mechanical Harness | 2800-0004-0012 | general | M4x1２ socket screws | M4x12 Socket Screw 25-pack | https://www.gobilda.com/2800-series-zinc-plated-steel-socket-head-screw-m4-x-0-7mm-12mm-length-25-pack/ | $3.19 | 1 | ongoing | 2023-10-01 | 2024-01-31 | 123
P10.019 | M4x16 socket screws-1 | Part | Mechanical Harness | 2800-0004-0016 | general | M4x16 socket screws | M4x16 Socket Screw 25-pack | https://www.gobilda.com/2800-series-zinc-plated-steel-socket-head-screw-m4-x-0-7mm-16mm-length-25-pack/ | $3.19 | 2 | ongoing | 2023-10-01 | 2024-01-31 | 123
P10.020 | M4x16 socket screws-2 | Part | Mechanical Harness | 2800-0004-0016 | general | M4x16 socket screws | M4x16 Socket Screw 25-pack | https://www.gobilda.com/2800-series-zinc-plated-steel-socket-head-screw-m4-x-0-7mm-16mm-length-25-pack/ | $3.19 | 2 | ongoing | 2023-10-01 | 2024-01-31 | 123
P10.021 | M4x20 socket screws-1 | Part | Mechanical Harness | 2800-0004-0020 | general | M4x20 socket screws | M4x20 Socket Screw 25-pack | https://www.gobilda.com/2800-series-zinc-plated-steel-socket-head-screw-m4-x-0-7mm-20mm-length-25-pack/ | $3.09 | 1 | closed | 2023-08-30 | 2023-12-30 | 123
P2.001 | wheel-1 | Part | Drive Wheel Assembly-2 | 5374X | drive wheel | wheel | Traxxas 5374X Talon Tires, Gemini Wheels, Black Chrome - Dollar Hobbyz | https://www.dollarhobbyz.com/collections/all/products/traxxas-2-talon-tires-gemini-black-chrome-wheels-5374x | $34.95 | 3 | closed | 2023-08-30 | 2023-12-30 | 123
P2.002 | clamping mount-1 | Part | Drive Wheel Assembly-2 | 1401-0043-0036 | drive wheel | clamping mount | 1401 Series 2-Side, 2-Post Clamping Mount (43mm Width, 36mm Bore) - goBILDA | https://www.gobilda.com/1401-series-2-side-2-post-clamping-mount-43mm-width-36mm-bore/ | $6.99 | 6 | closed | 2023-08-30 | 2023-12-30 | 123
P2.003 | motor-1 | Part | Drive Wheel Assembly-2 | 5203-2402-0027 | drive wheel | motor | 5203 Series Yellow Jacket Planetary Gear Motor (26.9:1 Ratio, 24mm Length 8mm REX™ Shaft, 223 RPM, 3.3 - 5V Encoder) | https://www.gobilda.com/5203-series-yellow-jacket-planetary-gear-motor-26-9-1-ratio-24mm-length-8mm-rex-shaft-223-rpm-3-3-5v-encoder/ | $42.99 | 6 | closed | 2023-08-30 | 2023-12-30 | 123
P2.004 | REX bore hub-1 | Part | Drive Wheel Assembly-2 | 1310-0016-4008 | drive wheel | REX bore hub | 1310 Series Hyper Hub (8mm REX™ Bore) | https://www.gobilda.com/1310-series-hyper-hub-8mm-rex-bore/ | $7.99 | 6 | closed | 2023-08-30 | 2023-12-30 | 123
P2.005 | 2 Hole U channel-1 | Part | Drive Wheel Assembly-2 | 1120-0002-0072 | drive wheel,body | 2 Hole U channel | 1120 Series U-Channel (2 Hole, 72mm Length) - goBILDA | https://www.gobilda.com/1120-series-u-channel-2-hole-72mm-length/ | $4.99 | 14 | closed | 2023-08-30 | 2023-12-30 | 123
P3.001 | wheel-1 | Part | Corner Wheel Assembly-1 | 5374X | drive wheel | wheel | Traxxas 5374X Talon Tires, Gemini Wheels, Black Chrome - Dollar Hobbyz | https://www.dollarhobbyz.com/collections/all/products/traxxas-2-talon-tires-gemini-black-chrome-wheels-5374x | $34.95 | 3 | closed | 2023-08-30 | 2023-12-30 | 123
P3.002 | clamping mount-1 | Part | Corner Wheel Assembly-1 | 1401-0043-0036 | drive wheel | clamping mount | 1401 Series 2-Side, 2-Post Clamping Mount (43mm Width, 36mm Bore) - goBILDA | https://www.gobilda.com/1401-series-2-side-2-post-clamping-mount-43mm-width-36mm-bore/ | $6.99 | 6 | closed | 2023-08-30 | 2023-12-30 | 123
P3.003 | motor-1 | Part | Corner Wheel Assembly-1 | 5203-2402-0027 | drive wheel | motor | 5203 Series Yellow Jacket Planetary Gear Motor (26.9:1 Ratio, 24mm Length 8mm REX™ Shaft, 223 RPM, 3.3 - 5V Encoder) | https://www.gobilda.com/5203-series-yellow-jacket-planetary-gear-motor-26-9-1-ratio-24mm-length-8mm-rex-shaft-223-rpm-3-3-5v-encoder/ | $42.99 | 6 | closed | 2023-08-30 | 2023-12-30 | 123
P3.004 | REX bore hub-1 | Part | Corner Wheel Assembly-1 | 1310-0016-4008 | drive wheel | REX bore hub | 1310 Series Hyper Hub (8mm REX™ Bore) | https://www.gobilda.com/1310-series-hyper-hub-8mm-rex-bore/ | $7.99 | 6 | closed | 2023-08-30 | 2023-12-30 | 123
P3.005 | 2 Hole U channel-1 | Part | Corner Wheel Assembly-1 | 1120-0002-0072 | drive wheel,body | 2 Hole U channel | 1120 Series U-Channel (2 Hole, 72mm Length) - goBILDA | https://www.gobilda.com/1120-series-u-channel-2-hole-72mm-length/ | $4.99 | 14 | closed | 2023-08-30 | 2023-12-30 | 123
P3.006 | 144mm goRail-1 | Part | Corner Wheel Assembly-1 | 1109-0024-0144 | corner | 144mm goRail | 1109 Series goRAIL (144mm Length) - goBILDA | https://www.gobilda.com/1109-series-gorail-144mm-length/ | $5.49 | 4 | closed | 2023-08-30 | 2023-12-30 | 123
P3.007 | 4 Hole U channel-1 | Part | Corner Wheel Assembly-1 | 1121-0004-0120 | corner | 4 Hole U channel | 1121 Series Low-Side U-Channel (4 Hole, 120mm Length) - goBILDA | https://www.gobilda.com/1121-series-low-side-u-channel-4-hole-120mm-length/ | $5.99 | 4 | closed | 2023-08-30 | 2023-12-30 | 123
P4.001 | wheel-1 | Part | Corner Wheel Assembly-2 | 5374X | drive wheel | wheel | Traxxas 5374X Talon Tires, Gemini Wheels, Black Chrome - Dollar Hobbyz | https://www.dollarhobbyz.com/collections/all/products/traxxas-2-talon-tires-gemini-black-chrome-wheels-5374x | $34.95 | 3 | closed | 2023-08-30 | 2023-12-30 | 123
P4.002 | clamping mount-1 | Part | Corner Wheel Assembly-2 | 1401-0043-0036 | drive wheel | clamping mount | 1401 Series 2-Side, 2-Post Clamping Mount (43mm Width, 36mm Bore) - goBILDA | https://www.gobilda.com/1401-series-2-side-2-post-clamping-mount-43mm-width-36mm-bore/ | $6.99 | 6 | closed | 2023-08-30 | 2023-12-30 | 123
P4.003 | motor-1 | Part | Corner Wheel Assembly-2 | 5203-2402-0027 | drive wheel | motor | 5203 Series Yellow Jacket Planetary Gear Motor (26.9:1 Ratio, 24mm Length 8mm REX™ Shaft, 223 RPM, 3.3 - 5V Encoder) | https://www.gobilda.com/5203-series-yellow-jacket-planetary-gear-motor-26-9-1-ratio-24mm-length-8mm-rex-shaft-223-rpm-3-3-5v-encoder/ | $42.99 | 6 | closed | 2023-08-30 | 2023-12-30 | 123
P4.004 | REX bore hub-1 | Part | Corner Wheel Assembly-2 | 1310-0016-4008 | drive wheel | REX bore hub | 1310 Series Hyper Hub (8mm REX™ Bore) | https://www.gobilda.com/1310-series-hyper-hub-8mm-rex-bore/ | $7.99 | 6 | ongoing | 2023-10-01 | 2024-01-31 | 123
P4.005 | 2 Hole U channel-1 | Part | Corner Wheel Assembly-2 | 1120-0002-0072 | drive wheel,body | 2 Hole U channel | 1120 Series U-Channel (2 Hole, 72mm Length) - goBILDA | https://www.gobilda.com/1120-series-u-channel-2-hole-72mm-length/ | $4.99 | 14 | ongoing | 2023-10-01 | 2024-01-31 | 123
P4.006 | 144mm goRail-1 | Part | Corner Wheel Assembly-2 | 1109-0024-0144 | corner | 144mm goRail | 1109 Series goRAIL (144mm Length) - goBILDA | https://www.gobilda.com/1109-series-gorail-144mm-length/ | $5.49 | 4 | ongoing | 2023-10-01 | 2024-01-31 | 123
P4.007 | 4 Hole U channel-1 | Part | Corner Wheel Assembly-2 | 1121-0004-0120 | corner | 4 Hole U channel | 1121 Series Low-Side U-Channel (4 Hole, 120mm Length) - goBILDA | https://www.gobilda.com/1121-series-low-side-u-channel-4-hole-120mm-length/ | $5.99 | 4 | ongoing | 2023-10-01 | 2024-01-31 | 123
P5.001 | wheel-1 | Part | Corner Wheel Assembly-3 | 5374X | drive wheel | wheel | Traxxas 5374X Talon Tires, Gemini Wheels, Black Chrome - Dollar Hobbyz | https://www.dollarhobbyz.com/collections/all/products/traxxas-2-talon-tires-gemini-black-chrome-wheels-5374x | $34.95 | 3 | ongoing | 2023-10-01 | 2024-01-31 | 123
P5.002 | clamping mount-1 | Part | Corner Wheel Assembly-3 | 1401-0043-0036 | drive wheel | clamping mount | 1401 Series 2-Side, 2-Post Clamping Mount (43mm Width, 36mm Bore) - goBILDA | https://www.gobilda.com/1401-series-2-side-2-post-clamping-mount-43mm-width-36mm-bore/ | $6.99 | 6 | ongoing | 2023-10-01 | 2024-01-31 | 123
P5.003 | motor-1 | Part | Corner Wheel Assembly-3 | 5203-2402-0027 | drive wheel | motor | 5203 Series Yellow Jacket Planetary Gear Motor (26.9:1 Ratio, 24mm Length 8mm REX™ Shaft, 223 RPM, 3.3 - 5V Encoder) | https://www.gobilda.com/5203-series-yellow-jacket-planetary-gear-motor-26-9-1-ratio-24mm-length-8mm-rex-shaft-223-rpm-3-3-5v-encoder/ | $42.99 | 6 | ongoing | 2023-10-01 | 2024-01-31 | 123
P5.004 | REX bore hub-1 | Part | Corner Wheel Assembly-3 | 1310-0016-4008 | drive wheel | REX bore hub | 1310 Series Hyper Hub (8mm REX™ Bore) | https://www.gobilda.com/1310-series-hyper-hub-8mm-rex-bore/ | $7.99 | 6 | ongoing | 2023-10-01 | 2024-01-31 | 123
P5.005 | 2 Hole U channel-1 | Part | Corner Wheel Assembly-3 | 1120-0002-0072 | drive wheel,body | 2 Hole U channel | 1120 Series U-Channel (2 Hole, 72mm Length) - goBILDA | https://www.gobilda.com/1120-series-u-channel-2-hole-72mm-length/ | $4.99 | 14 | ongoing | 2023-10-01 | 2024-01-31 | 123
P5.006 | 144mm goRail-1 | Part | Corner Wheel Assembly-3 | 1109-0024-0144 | corner | 144mm goRail | 1109 Series goRAIL (144mm Length) - goBILDA | https://www.gobilda.com/1109-series-gorail-144mm-length/ | $5.49 | 4 | ongoing | 2023-10-01 | 2024-01-31 | 123
P5.007 | 4 Hole U channel-1 | Part | Corner Wheel Assembly-3 | 1121-0004-0120 | corner | 4 Hole U channel | 1121 Series Low-Side U-Channel (4 Hole, 120mm Length) - goBILDA | https://www.gobilda.com/1121-series-low-side-u-channel-4-hole-120mm-length/ | $5.99 | 4 | ongoing | 2023-10-01 | 2024-01-31 | 123
P6.001 | wheel-1 | Part | Corner Wheel Assembly-4 | 5374X | drive wheel | wheel | Traxxas 5374X Talon Tires, Gemini Wheels, Black Chrome - Dollar Hobbyz | https://www.dollarhobbyz.com/collections/all/products/traxxas-2-talon-tires-gemini-black-chrome-wheels-5374x | $34.95 | 3 | ongoing | 2023-10-01 | 2024-01-31 | 123
P6.002 | clamping mount-1 | Part | Corner Wheel Assembly-4 | 1401-0043-0036 | drive wheel | clamping mount | 1401 Series 2-Side, 2-Post Clamping Mount (43mm Width, 36mm Bore) - goBILDA | https://www.gobilda.com/1401-series-2-side-2-post-clamping-mount-43mm-width-36mm-bore/ | $6.99 | 6 | ongoing | 2023-10-01 | 2024-01-31 | 123
P6.003 | motor-1 | Part | Corner Wheel Assembly-4 | 5203-2402-0027 | drive wheel | motor | 5203 Series Yellow Jacket Planetary Gear Motor (26.9:1 Ratio, 24mm Length 8mm REX™ Shaft, 223 RPM, 3.3 - 5V Encoder) | https://www.gobilda.com/5203-series-yellow-jacket-planetary-gear-motor-26-9-1-ratio-24mm-length-8mm-rex-shaft-223-rpm-3-3-5v-encoder/ | $42.99 | 6 | ongoing | 2023-10-01 | 2024-01-31 | 123
P6.004 | REX bore hub-1 | Part | Corner Wheel Assembly-4 | 1310-0016-4008 | drive wheel | REX bore hub | 1310 Series Hyper Hub (8mm REX™ Bore) | https://www.gobilda.com/1310-series-hyper-hub-8mm-rex-bore/ | $7.99 | 6 | ongoing | 2023-10-01 | 2024-01-31 | 123
P6.005 | 2 Hole U channel-1 | Part | Corner Wheel Assembly-4 | 1120-0002-0072 | drive wheel,body | 2 Hole U channel | 1120 Series U-Channel (2 Hole, 72mm Length) - goBILDA | https://www.gobilda.com/1120-series-u-channel-2-hole-72mm-length/ | $4.99 | 14 | ongoing | 2023-10-01 | 2024-01-31 | 123
P6.006 | 144mm goRail-1 | Part | Corner Wheel Assembly-4 | 1109-0024-0144 | corner | 144mm goRail | 1109 Series goRAIL (144mm Length) - goBILDA | https://www.gobilda.com/1109-series-gorail-144mm-length/ | $5.49 | 4 | ongoing | 2023-10-01 | 2024-01-31 | 123
P6.007 | 4 Hole U channel-1 | Part | Corner Wheel Assembly-4 | 1121-0004-0120 | corner | 4 Hole U channel | 1121 Series Low-Side U-Channel (4 Hole, 120mm Length) - goBILDA | https://www.gobilda.com/1121-series-low-side-u-channel-4-hole-120mm-length/ | $5.99 | 4 | ongoing | 2023-10-01 | 2024-01-31 | 123
P8.001 | 1hole uchannel-1 | Part | Rocker Bogie Suspension Assembly-1 | 1120-0001-0048 | rocker bogie | 1hole uchannel | 1120 Series U-Channel (1 Hole, 48mm Length) - goBILDA | https://www.gobilda.com/1120-series-u-channel-1-hole-48mm-length/ | $3.69 | 2 | ongoing | 2023-10-01 | 2024-01-31 | 123
P8.002 | servoblock-1 | Part | Rocker Bogie Suspension Assembly-1 | 3202-0001-2501 | rocker bogie | servoblock | ServoBlock™ (Standard Size, 25 Tooth Spline, Hub Shaft) - goBILDA | https://www.gobilda.com/servoblock-standard-size-25-tooth-spline-hub-shaft/ | $29.99 | 4 | closed | 2023-08-30 | 2023-12-30 | 123
P8.003 | servoblock-2 | Part | Rocker Bogie Suspension Assembly-1 | 3202-0001-2501 | rocker bogie | servoblock | ServoBlock™ (Standard Size, 25 Tooth Spline, Hub Shaft) - goBILDA | https://www.gobilda.com/servoblock-standard-size-25-tooth-spline-hub-shaft/ | $29.99 | 4 | closed | 2023-08-30 | 2023-12-30 | 123
P8.004 | servo-1 | Part | Rocker Bogie Suspension Assembly-1 | 2000-0025-0002 | rocker bogie | servo | 2000 Series Dual Mode Servo (25-2, Torque) - goBILDA | https://www.gobilda.com/2000-series-dual-mode-servo-25-2-torque/ | $31.99 | 4 | closed | 2023-08-30 | 2023-12-30 | 123
P8.005 | servo-2 | Part | Rocker Bogie Suspension Assembly-1 | 2000-0025-0002 | rocker bogie | servo | 2000 Series Dual Mode Servo (25-2, Torque) - goBILDA | https://www.gobilda.com/2000-series-dual-mode-servo-25-2-torque/ | $31.99 | 4 | closed | 2023-08-30 | 2023-12-30 | 123
P8.006 | 8mm Sonic Hub-1 | Part | Rocker Bogie Suspension Assembly-1 | 1309-0016-0008 | rocker bogie | 8mm Sonic Hub | 1309 Series Sonic Hub (8mm Bore) - goBILDA | https://www.gobilda.com/1309-series-sonic-hub-8mm-bore/ | $6.99 | 2 | closed | 2023-08-30 | 2023-12-30 | 123
P8.007 | flanged bearing 2pack-1 | Part | Rocker Bogie Suspension Assembly-1 | 1611-0514-0008 | rocker bogie | flanged bearing 2pack | 1611 Series Flanged Ball Bearing (8mm ID x 14mm OD, 5mm Thickness) - 2 Pack - goBILDA | https://www.gobilda.com/1611-series-flanged-ball-bearing-8mm-id-x-14mm-od-5mm-thickness-2-pack/ | $3.99 | 2 | closed | 2023-08-30 | 2023-12-30 | 123
P8.008 | joint pattern spacer-1 | Part | Rocker Bogie Suspension Assembly-1 | 1504-0032-0020 | rocker bogie | joint pattern spacer | 1504 Series 32mm OD Pattern Spacer (2mm Length) - goBILDA | https://www.gobilda.com/1504-series-32mm-od-pattern-spacer-2mm-length/ | $1.99 | 4 | closed | 2023-08-30 | 2023-12-30 | 123
P8.009 | joint pattern spacer-2 | Part | Rocker Bogie Suspension Assembly-1 | 1504-0032-0020 | rocker bogie | joint pattern spacer | 1504 Series 32mm OD Pattern Spacer (2mm Length) - goBILDA | https://www.gobilda.com/1504-series-32mm-od-pattern-spacer-2mm-length/ | $1.99 | 4 | closed | 2023-08-30 | 2023-12-30 | 123
P8.010 | joint 8mm shaft-1 | Part | Rocker Bogie Suspension Assembly-1 | 2100-0008-0050 | rocker bogie | joint 8mm shaft | 2100 Series Stainless Steel Round Shaft (8mm Diameter, 50mm Length) | https://www.gobilda.com/2100-series-stainless-steel-round-shaft-8mm-diameter-50mm-length/ | $1.49 | 2 | closed | 2023-08-30 | 2023-12-30 | 123
P8.011 | joint 3hole flat beam 2pack-1 | Part | Rocker Bogie Suspension Assembly-1 | 1102-0003-0024 | rocker bogie | joint 3hole flat beam 2pack | 1102 Series Flat Beam (3 Hole, 24mm Length) - 2 Pack - goBILDA | https://www.gobilda.com/1102-series-flat-beam-3-hole-24mm-length-2-pack/ | $1.89 | 4 | closed | 2023-08-30 | 2023-12-30 | 123
P8.012 | joint 3hole flat beam 2pack-2 | Part | Rocker Bogie Suspension Assembly-1 | 1102-0003-0024 | rocker bogie | joint 3hole flat beam 2pack | 1102 Series Flat Beam (3 Hole, 24mm Length) - 2 Pack - goBILDA | https://www.gobilda.com/1102-series-flat-beam-3-hole-24mm-length-2-pack/ | $1.89 | 4 | closed | 2023-08-30 | 2023-12-30 | 123
P8.013 | joint pattern mount-1 | Part | Rocker Bogie Suspension Assembly-1 | 1221-0032-0002 | rocker bogie | joint pattern mount | 1221 Series 2-Side, 2-Post Pattern Mount (32-2) - goBILDA | https://www.gobilda.com/1221-series-2-side-2-post-pattern-mount-32-2/ | $4.99 | 4 | closed | 2023-08-30 | 2023-12-30 | 123
P8.014 | joint pattern mount-2 | Part | Rocker Bogie Suspension Assembly-1 | 1221-0032-0002 | rocker bogie | joint pattern mount | 1221 Series 2-Side, 2-Post Pattern Mount (32-2) - goBILDA | https://www.gobilda.com/1221-series-2-side-2-post-pattern-mount-32-2/ | $4.99 | 4 | closed | 2023-08-30 | 2023-12-30 | 123
P8.015 | steel flat bracket-1 | Part | Rocker Bogie Suspension Assembly-1 | 1126-0001-0001 | rocker bogie | steel flat bracket | 1126 Series Steel Flat Bracket (1-1) - 2 Pack - goBILDA | https://www.gobilda.com/1126-series-steel-flat-bracket-1-1-2-pack/ | $2.49 | 2 | ongoing | 2023-10-01 | 2025-08-28 | 698
P8.016 | 3x5 grid plate-1 | Part | Rocker Bogie Suspension Assembly-1 | 1116-0024-0040 | rocker bogie,body | 3x5 grid plate | 1116 Series Grid Plate (3 x 5 Hole, 24 x 40mm) - goBILDA | https://www.gobilda.com/1116-series-grid-plate-3-x-5-hole-24-x-40mm/ | $1.29 | 8 | ongoing | 2023-10-01 | 2025-08-28 | 698
P8.017 | 3x5 grid plate-2 | Part | Rocker Bogie Suspension Assembly-1 | 1116-0024-0040 | rocker bogie,body | 3x5 grid plate | 1116 Series Grid Plate (3 x 5 Hole, 24 x 40mm) - goBILDA | https://www.gobilda.com/1116-series-grid-plate-3-x-5-hole-24-x-40mm/ | $1.29 | 8 | ongoing | 2023-10-01 | 2025-08-28 | 698
P8.018 | angle bracket-1 | Part | Rocker Bogie Suspension Assembly-1 | 1111-0003-0001 | rocker bogie | angle bracket | 1111 Series Angle Pattern Bracket (3-1) - goBILDA | https://www.gobilda.com/1111-series-angle-pattern-bracket-3-1/ | $5.99 | 2 | ongoing | 2023-10-01 | 2025-08-28 | 698
P8.019 | 96mm open goRail-1 | Part | Rocker Bogie Suspension Assembly-1 | 1118-0024-0096 | rocker bogie | 96mm open goRail | 1118 Series Open goRAIL (96mm Length) - goBILDA | https://www.gobilda.com/1118-series-open-gorail-96mm-length/ | $3.39 | 6 | ongoing | 2023-10-01 | 2025-08-28 | 698
P8.020 | 96mm open goRail-2 | Part | Rocker Bogie Suspension Assembly-1 | 1118-0024-0096 | rocker bogie | 96mm open goRail | 1118 Series Open goRAIL (96mm Length) - goBILDA | https://www.gobilda.com/1118-series-open-gorail-96mm-length/ | $3.39 | 6 | ongoing | 2023-10-01 | 2025-08-28 | 698
P8.021 | 96mm open goRail-3 | Part | Rocker Bogie Suspension Assembly-1 | 1118-0024-0096 | rocker bogie | 96mm open goRail | 1118 Series Open goRAIL (96mm Length) - goBILDA | https://www.gobilda.com/1118-series-open-gorail-96mm-length/ | $3.39 | 6 | ongoing | 2023-10-01 | 2025-08-28 | 698
P8.022 | 288mm open goRail-1 | Part | Rocker Bogie Suspension Assembly-1 | 1118-0024-0288 | rocker bogie | 288mm open goRail | 1118 Series Open goRAIL (288mm Length) - goBILDA | https://www.gobilda.com/1118-series-open-gorail-288mm-length/ | $5.89 | 2 | ongoing | 2023-10-01 | 2025-08-28 | 698
P8.023 | 45deg bracket-1 | Part | Rocker Bogie Suspension Assembly-1 | 1111-0001-0001 | rocker bogie | 45deg bracket | 1111 Series Angle Pattern Bracket (1-1) - goBILDA | https://www.gobilda.com/1111-series-angle-pattern-bracket-1-1/ | $2.99 | 4 | ongoing | 2023-10-01 | 2025-08-28 | 698
P8.024 | 45deg bracket-2 | Part | Rocker Bogie Suspension Assembly-1 | 1111-0001-0001 | rocker bogie | 45deg bracket | 1111 Series Angle Pattern Bracket (1-1) - goBILDA | https://www.gobilda.com/1111-series-angle-pattern-bracket-1-1/ | $2.99 | 4 | ongoing | 2023-10-01 | 2025-08-28 | 698
P8.025 | 90deg steel bracket 2pack-1 | Part | Rocker Bogie Suspension Assembly-1 | 1137-0001-0001 | rocker bogie | 90deg steel bracket 2pack | 1137 Series Steel Flat Grid Bracket (1-1) - 2 Pack - goBILDA | https://www.gobilda.com/1137-series-steel-flat-grid-bracket-1-1-2-pack/ | $3.49 | 1 | ongoing | 2023-10-01 | 2025-08-28 | 698
P8.026 | control arm-1 | Part | Rocker Bogie Suspension Assembly-1 | 1916-0014-0072 | rocker bogie | control arm | Plastic Hub-Mount Control Arm (72mm Length) - goBILDA | https://www.gobilda.com/plastic-hub-mount-control-arm-72mm-length/ | $4.99 | 4 | ongoing | 2023-10-01 | 2025-08-28 | 698
P8.027 | control arm-2 | Part | Rocker Bogie Suspension Assembly-1 | 1916-0014-0072 | rocker bogie | control arm | Plastic Hub-Mount Control Arm (72mm Length) - goBILDA | https://www.gobilda.com/plastic-hub-mount-control-arm-72mm-length/ | $4.99 | 4 | ongoing | 2023-10-01 | 2025-08-28 | 698
P8.028 | 8mm ID Spacer (10mm OD, 6mm Length)-1 | Part | Rocker Bogie Suspension Assembly-1 | 1514-0010-0060 | rocker bogie | 8mm ID Spacer (10mm OD, 6mm Length) | 1514 Series 8mm ID Spacer (10mm OD, 6mm Length) - 4 Pack - goBILDA | https://www.gobilda.com/1514-series-8mm-id-spacer-10mm-od-6mm-length-4-pack/ | $2.19 | 1 | ongoing | 2023-10-01 | 2025-08-28 | 698
P8.029 | 8mm ID Spacer (10mm OD, 4mm Length)-1 | Part | Rocker Bogie Suspension Assembly-1 | 1522-0010-0040 | rocker bogie | 8mm ID Spacer (10mm OD, 4mm Length) | 1522 Series 8mm ID Spacer (10mm OD, 4mm Length) - 4 Pack - goBILDA | https://www.gobilda.com/1522-series-8mm-id-spacer-10mm-od-4mm-length-4-pack/ | $2.99 | 1 | ongoing | 2023-10-01 | 2025-08-28 | 698
P9.001 | 1hole uchannel-1 | Part | Rocker Bogie Suspension Assembly-2 | 1120-0001-0048 | rocker bogie | 1hole uchannel | 1120 Series U-Channel (1 Hole, 48mm Length) - goBILDA | https://www.gobilda.com/1120-series-u-channel-1-hole-48mm-length/ | $3.69 | 2 | ongoing | 2023-10-01 | 2025-08-28 | 698
P9.002 | servoblock-1 | Part | Rocker Bogie Suspension Assembly-2 | 3202-0001-2501 | rocker bogie | servoblock | ServoBlock™ (Standard Size, 25 Tooth Spline, Hub Shaft) - goBILDA | https://www.gobilda.com/servoblock-standard-size-25-tooth-spline-hub-shaft/ | $29.99 | 4 | ongoing | 2023-10-01 | 2025-08-28 | 698
P9.003 | servoblock-2 | Part | Rocker Bogie Suspension Assembly-2 | 3202-0001-2501 | rocker bogie | servoblock | ServoBlock™ (Standard Size, 25 Tooth Spline, Hub Shaft) - goBILDA | https://www.gobilda.com/servoblock-standard-size-25-tooth-spline-hub-shaft/ | $29.99 | 4 | ongoing | 2023-10-01 | 2025-08-28 | 698
P9.004 | servo-1 | Part | Rocker Bogie Suspension Assembly-2 | 2000-0025-0002 | rocker bogie | servo | 2000 Series Dual Mode Servo (25-2, Torque) - goBILDA | https://www.gobilda.com/2000-series-dual-mode-servo-25-2-torque/ | $31.99 | 4 | ongoing | 2023-10-01 | 2025-08-28 | 698
P9.005 | servo-2 | Part | Rocker Bogie Suspension Assembly-2 | 2000-0025-0002 | rocker bogie | servo | 2000 Series Dual Mode Servo (25-2, Torque) - goBILDA | https://www.gobilda.com/2000-series-dual-mode-servo-25-2-torque/ | $31.99 | 4 | ongoing | 2023-10-01 | 2025-08-28 | 698
P9.006 | 8mm Sonic Hub-1 | Part | Rocker Bogie Suspension Assembly-2 | 1309-0016-0008 | rocker bogie | 8mm Sonic Hub | 1309 Series Sonic Hub (8mm Bore) - goBILDA | https://www.gobilda.com/1309-series-sonic-hub-8mm-bore/ | $6.99 | 2 | ongoing | 2023-10-01 | 2025-08-28 | 698
P9.007 | flanged bearing 2pack-1 | Part | Rocker Bogie Suspension Assembly-2 | 1611-0514-0008 | rocker bogie | flanged bearing 2pack | 1611 Series Flanged Ball Bearing (8mm ID x 14mm OD, 5mm Thickness) - 2 Pack - goBILDA | https://www.gobilda.com/1611-series-flanged-ball-bearing-8mm-id-x-14mm-od-5mm-thickness-2-pack/ | $3.99 | 2 | ongoing | 2023-10-01 | 2025-08-28 | 698
P9.008 | joint pattern spacer-1 | Part | Rocker Bogie Suspension Assembly-2 | 1504-0032-0020 | rocker bogie | joint pattern spacer | 1504 Series 32mm OD Pattern Spacer (2mm Length) - goBILDA | https://www.gobilda.com/1504-series-32mm-od-pattern-spacer-2mm-length/ | $1.99 | 4 | ongoing | 2023-10-01 | 2025-08-28 | 698
P9.009 | joint pattern spacer-2 | Part | Rocker Bogie Suspension Assembly-2 | 1504-0032-0020 | rocker bogie | joint pattern spacer | 1504 Series 32mm OD Pattern Spacer (2mm Length) - goBILDA | https://www.gobilda.com/1504-series-32mm-od-pattern-spacer-2mm-length/ | $1.99 | 4 | ongoing | 2023-10-01 | 2025-08-28 | 698
P9.010 | joint 8mm shaft-1 | Part | Rocker Bogie Suspension Assembly-2 | 2100-0008-0050 | rocker bogie | joint 8mm shaft | 2100 Series Stainless Steel Round Shaft (8mm Diameter, 50mm Length) | https://www.gobilda.com/2100-series-stainless-steel-round-shaft-8mm-diameter-50mm-length/ | $1.49 | 2 | ongoing | 2023-10-01 | 2025-08-28 | 698
P9.011 | joint 3hole flat beam 2pack-1 | Part | Rocker Bogie Suspension Assembly-2 | 1102-0003-0024 | rocker bogie | joint 3hole flat beam 2pack | 1102 Series Flat Beam (3 Hole, 24mm Length) - 2 Pack - goBILDA | https://www.gobilda.com/1102-series-flat-beam-3-hole-24mm-length-2-pack/ | $1.89 | 4 | ongoing | 2023-10-01 | 2025-08-28 | 698
P9.012 | joint 3hole flat beam 2pack-2 | Part | Rocker Bogie Suspension Assembly-2 | 1102-0003-0024 | rocker bogie | joint 3hole flat beam 2pack | 1102 Series Flat Beam (3 Hole, 24mm Length) - 2 Pack - goBILDA | https://www.gobilda.com/1102-series-flat-beam-3-hole-24mm-length-2-pack/ | $1.89 | 4 | ongoing | 2023-10-01 | 2025-08-28 | 698
P9.013 | joint pattern mount-1 | Part | Rocker Bogie Suspension Assembly-2 | 1221-0032-0002 | rocker bogie | joint pattern mount | 1221 Series 2-Side, 2-Post Pattern Mount (32-2) - goBILDA | https://www.gobilda.com/1221-series-2-side-2-post-pattern-mount-32-2/ | $4.99 | 4 | closed | 2023-08-30 | 2023-12-30 | 123
P9.014 | joint pattern mount-2 | Part | Rocker Bogie Suspension Assembly-2 | 1221-0032-0002 | rocker bogie | joint pattern mount | 1221 Series 2-Side, 2-Post Pattern Mount (32-2) - goBILDA | https://www.gobilda.com/1221-series-2-side-2-post-pattern-mount-32-2/ | $4.99 | 4 | closed | 2023-08-30 | 2023-12-30 | 123
P9.015 | steel flat bracket-1 | Part | Rocker Bogie Suspension Assembly-2 | 1126-0001-0001 | rocker bogie | steel flat bracket | 1126 Series Steel Flat Bracket (1-1) - 2 Pack - goBILDA | https://www.gobilda.com/1126-series-steel-flat-bracket-1-1-2-pack/ | $2.49 | 2 | closed | 2023-08-30 | 2023-12-30 | 123
P9.016 | 3x5 grid plate-1 | Part | Rocker Bogie Suspension Assembly-2 | 1116-0024-0040 | rocker bogie,body | 3x5 grid plate | 1116 Series Grid Plate (3 x 5 Hole, 24 x 40mm) - goBILDA | https://www.gobilda.com/1116-series-grid-plate-3-x-5-hole-24-x-40mm/ | $1.29 | 8 | closed | 2023-08-30 | 2023-12-30 | 123
P9.017 | 3x5 grid plate-2 | Part | Rocker Bogie Suspension Assembly-2 | 1116-0024-0040 | rocker bogie,body | 3x5 grid plate | 1116 Series Grid Plate (3 x 5 Hole, 24 x 40mm) - goBILDA | https://www.gobilda.com/1116-series-grid-plate-3-x-5-hole-24-x-40mm/ | $1.29 | 8 | closed | 2023-08-30 | 2023-12-30 | 123
P9.018 | angle bracket-1 | Part | Rocker Bogie Suspension Assembly-2 | 1111-0003-0001 | rocker bogie | angle bracket | 1111 Series Angle Pattern Bracket (3-1) - goBILDA | https://www.gobilda.com/1111-series-angle-pattern-bracket-3-1/ | $5.99 | 2 | closed | 2023-08-30 | 2023-12-30 | 123
P9.019 | 96mm open goRail-1 | Part | Rocker Bogie Suspension Assembly-2 | 1118-0024-0096 | rocker bogie | 96mm open goRail | 1118 Series Open goRAIL (96mm Length) - goBILDA | https://www.gobilda.com/1118-series-open-gorail-96mm-length/ | $3.39 | 6 | closed | 2023-08-30 | 2023-12-30 | 123
P9.020 | 96mm open goRail-2 | Part | Rocker Bogie Suspension Assembly-2 | 1118-0024-0096 | rocker bogie | 96mm open goRail | 1118 Series Open goRAIL (96mm Length) - goBILDA | https://www.gobilda.com/1118-series-open-gorail-96mm-length/ | $3.39 | 6 | closed | 2023-08-30 | 2023-12-30 | 123
P9.021 | 96mm open goRail-3 | Part | Rocker Bogie Suspension Assembly-2 | 1118-0024-0096 | rocker bogie | 96mm open goRail | 1118 Series Open goRAIL (96mm Length) - goBILDA | https://www.gobilda.com/1118-series-open-gorail-96mm-length/ | $3.39 | 6 | closed | 2023-08-30 | 2023-12-30 | 123
P9.022 | 288mm open goRail-1 | Part | Rocker Bogie Suspension Assembly-2 | 1118-0024-0288 | rocker bogie | 288mm open goRail | 1118 Series Open goRAIL (288mm Length) - goBILDA | https://www.gobilda.com/1118-series-open-gorail-288mm-length/ | $5.89 | 2 | closed | 2023-08-30 | 2023-12-30 | 123
P9.023 | 45deg bracket-1 | Part | Rocker Bogie Suspension Assembly-2 | 1111-0001-0001 | rocker bogie | 45deg bracket | 1111 Series Angle Pattern Bracket (1-1) - goBILDA | https://www.gobilda.com/1111-series-angle-pattern-bracket-1-1/ | $2.99 | 4 | closed | 2023-08-30 | 2023-12-30 | 123
P9.024 | 45deg bracket-2 | Part | Rocker Bogie Suspension Assembly-2 | 1111-0001-0001 | rocker bogie | 45deg bracket | 1111 Series Angle Pattern Bracket (1-1) - goBILDA | https://www.gobilda.com/1111-series-angle-pattern-bracket-1-1/ | $2.99 | 4 | closed | 2023-08-30 | 2023-12-30 | 123
P9.025 | 90deg steel bracket 2pack-1 | Part | Rocker Bogie Suspension Assembly-2 | 1137-0001-0001 | rocker bogie | 90deg steel bracket 2pack | 1137 Series Steel Flat Grid Bracket (1-1) - 2 Pack - goBILDA | https://www.gobilda.com/1137-series-steel-flat-grid-bracket-1-1-2-pack/ | $3.49 | 1 | closed | 2023-08-30 | 2023-12-30 | 123
P9.026 | control arm-1 | Part | Rocker Bogie Suspension Assembly-2 | 1916-0014-0072 | rocker bogie | control arm | Plastic Hub-Mount Control Arm (72mm Length) - goBILDA | https://www.gobilda.com/plastic-hub-mount-control-arm-72mm-length/ | $4.99 | 4 | closed | 2023-08-30 | 2023-12-30 | 123
P9.027 | control arm-2 | Part | Rocker Bogie Suspension Assembly-2 | 1916-0014-0072 | rocker bogie | control arm | Plastic Hub-Mount Control Arm (72mm Length) - goBILDA | https://www.gobilda.com/plastic-hub-mount-control-arm-72mm-length/ | $4.99 | 4 | closed | 2023-08-30 | 2023-12-30 | 123
P9.028 | 8mm ID Spacer (10mm OD, 6mm Length)-1 | Part | Rocker Bogie Suspension Assembly-2 | 1514-0010-0060 | rocker bogie | 8mm ID Spacer (10mm OD, 6mm Length) | 1514 Series 8mm ID Spacer (10mm OD, 6mm Length) - 4 Pack - goBILDA | https://www.gobilda.com/1514-series-8mm-id-spacer-10mm-od-6mm-length-4-pack/ | $2.19 | 1 | closed | 2023-08-30 | 2023-12-30 | 123
P9.029 | 8mm ID Spacer (10mm OD, 4mm Length)-1 | Part | Rocker Bogie Suspension Assembly-2 | 1522-0010-0040 | rocker bogie | 8mm ID Spacer (10mm OD, 4mm Length) | 1522 Series 8mm ID Spacer (10mm OD, 4mm Length) - 4 Pack - goBILDA | https://www.gobilda.com/1522-series-8mm-id-spacer-10mm-od-4mm-length-4-pack/ | $2.99 | 1 | closed | 2023-08-30 | 2023-12-30 | 123